## Slide 1
UNIT 3
Managing Software Project

## Slide 2: Content
Software Metrices (Process, Product and Project Metrices)
Software Project Estimations
Software Project Planning (MS Project Tool)
Project Scheduling and Tracking
Risk Analysis & Management (Risk Identification, Risk Projection, Risk refinement, Risk Mitigation)
Unit 3

## Slide 3: The Four P’s
People — the most important element of a successful project
Product — the software to be built
Process — the set of framework activities and software engineering tasks to get the job done
Project — all work required to make the product a reality
Unit 3

## Slide 4
People includes:
  The stakeholders
  Team Leaders
  Software Team
  Agile Teams
  Coordination and communication Issues
Product includes:
  Software Scope
  Problem Decomposition
Process includes:
  Melding the product and the process
  Process Decomposition
Project includes:
  Start on the right foot
  Maintain momentum
  Track progress
  Make smart decisions
  Conduct a postmortem analysis
Unit 3

## Slide 5: Stakeholders
Senior managers who define the business issues that often have significant influence on the project.
Project (technical) managers who must plan, motivate, organize, and control the practitioners who do software work.
Practitioners who deliver the technical skills that are necessary to engineer a product or application.
Customers who specify the requirements for the software to be engineered and other stakeholders who have a peripheral interest in the outcome.
End-users who interact with the software once it is released for production use.
Unit 3

## Slide 6: Software Teams
How to lead?
How to organize?
How to motivate?
How to collaborate?
How to create good ideas?
Unit 3

## Slide 7: Team Leader
The MOI Model
  Motivation. The ability to encourage (by “push or pull”) technical people to produce to their best ability.
  Organization. The ability to mold existing processes (or invent new ones) that will enable the initial concept to be translated into a final product.
  Ideas or innovation. The ability to encourage people to create and feel creative even when they must work within bounds established for a particular software product or application.
Unit 3

## Slide 8: Software Teams
the difficulty of the problem to be solved
the size of the resultant program(s) in lines of code or function points
the time that the team will stay together (team lifetime)
the degree to which the problem can be modularized
the required quality and reliability of the system to be built
the rigidity of the delivery date
the degree of sociability (communication) required for the project
Unit 3

## Slide 9: Agile Teams
Team members must have trust in one another.
The distribution of skills must be appropriate to the problem.
Mavericks may have to be excluded from the team, if team cohesiveness is to be maintained.
Team is “self-organizing”
  An adaptive team structure
  Uses elements of Constantine’s random, open, and synchronous paradigms
  Significant autonomy
Unit 3

## Slide 10: Team Coordination & Communication
Formal, impersonal approaches include software engineering documents and work products (including source code), technical memos, project milestones, schedules, and project control tools (Chapter 23), change requests and related documentation, error tracking reports, and repository data (see Chapter 26).
Formal, interpersonal procedures focus on quality assurance activities (Chapter 25) applied to software engineering work products. These include status review meetings and design and code inspections.
Informal, interpersonal procedures include group meetings for information dissemination and problem solving and “collocation of requirements and development staff.”
Electronic communication encompasses electronic mail, electronic bulletin boards, and by extension, video-based conferencing systems.
Interpersonal networking includes informal discussions with team members and those outside the project who may have experience or insight that can assist team members.
Unit 3

## Slide 11: The Product Scope
Scope
    Context. How does the software to be built fit into a larger system, product, or business context and what constraints are imposed as a result of the context?
    Information objectives. What customer-visible data objects (Chapter 8) are produced as output from the software? What data objects are required for input?
    Function and performance. What function does the software perform to transform input data into output? Are any special performance characteristics to be addressed?
Software project scope must be unambiguous and understandable at the management and technical levels.

## Slide 12: Problem Decomposition
Sometimes called partitioning or problem elaboration
Once scope is defined …
  It is decomposed into constituent functions
  It is decomposed into user-visible data objects
  or
  It is decomposed into a set of problem classes
Decomposition process continues until all functions or problem classes have been defined
Unit 3

## Slide 13: Product Metrices
Focus on the quality of deliverables
Product metrics are combined across several projects to produce process metrics
Metrics for the product:
– Measures of the Analysis Model
– Complexity of the Design Model
– Internal algorithmic complexity
– Architectural complexity
– Data flow complexity
– Code metrics
Unit 3

## Slide 14: McCall’s Triangle of Quality
M
a
i
n
t
a
i
n
a
b
i
l
i
t
y
M
a
i
n
t
a
i
n
a
b
i
l
i
t
y
F
l
e
x
i
b
i
l
i
t
y
F
l
e
x
i
b
i
l
i
t
y
T
e
s
t
a
b
i
l
i
t
y
T
e
s
t
a
b
i
l
i
t
y
P
o
r
t
a
b
i
l
i
t
y
P
o
r
t
a
b
i
l
i
t
y
R
e
u
s
a
b
i
l
i
t
y
R
e
u
s
a
b
i
l
i
t
y
I
n
t
e
r
o
p
e
r
a
b
i
l
i
t
y
I
n
t
e
r
o
p
e
r
a
b
i
l
i
t
y
C
o
r
r
e
c
t
n
e
s
s
C
o
r
r
e
c
t
n
e
s
s
R
e
l
i
a
b
i
l
i
t
y
R
e
l
i
a
b
i
l
i
t
y
E
f
f
i
c
i
e
n
c
y
E
f
f
i
c
i
e
n
c
y
I
n
t
e
g
r
i
t
y
I
n
t
e
g
r
i
t
y
U
s
a
b
i
l
i
t
y
U
s
a
b
i
l
i
t
y
P
R
O
D
U
C
T
T
R
A
N
S
I
T
I
O
N
P
R
O
D
U
C
T
T
R
A
N
S
I
T
I
O
N
P
R
O
D
U
C
T
R
E
V
I
S
I
O
N
P
R
O
D
U
C
T
R
E
V
I
S
I
O
N
P
R
O
D
U
C
T
O
P
E
R
A
T
I
O
N
P
R
O
D
U
C
T
O
P
E
R
A
T
I
O
N
Unit 3

## Slide 15: The Process
Once a process framework has been established
  Consider project characteristics
  Determine the degree of rigor required
  Define a task set for each software engineering activity
    Task set =
      Software engineering tasks
      Work products
      Quality assurance points
      Milestones
Unit 3

## Slide 16: Process Metrics
Process metrics are collected across all projects and over long periods of time. Their intent is to provide a set of process indicators that lead to long-term software process improvement.
Focus on quality achieved as a consequence of a repeatable or managed process.
Strategic and Long Term.
Statistical Software Process Improvement (SSPI).
Error Categorization and Analysis:
– All errors and defects are categorized by origin
– The cost to correct each error and defect is recorded
– The number of errors and defects in each category is computed
– Data is analyzed to find categories that result in the highest cost to the organization
– Plans are developed to modify the process
Unit 3

## Slide 17: The Project
Projects get into trouble when …
  Software people don’t understand their customer’s needs.
  The product scope is poorly defined.
  Changes are managed poorly.
  The chosen technology changes.
  Business needs change [or are ill-defined].
  Deadlines are unrealistic.
  Users are resistant.
  Sponsorship is lost [or was never properly obtained].
  The project team lacks people with appropriate skills.
  Managers [and practitioners] avoid best practices and lessons learned.
Unit 3

## Slide 18: Common-Sense Approach to Projects
Start on the right foot. This is accomplished by working hard (very hard) to understand the problem that is to be solved and then setting realistic objectives and expectations.
Maintain momentum. The project manager must provide incentives to keep turnover of personnel to an absolute minimum, the team should emphasize quality in every task it performs, and senior management should do everything possible to stay out of the team’s way.
Track progress. For a software project, progress is tracked as work products (e.g., models, source code, sets of test cases) are produced and approved (using formal technical reviews) as part of a quality assurance activity.
Make smart decisions. In essence, the decisions of the project manager and the software team should be to “keep it simple.”
Conduct a postmortem analysis. Establish a consistent mechanism for extracting lessons learned for each project.
Unit 3

## Slide 19: Project Metrices
Project metrics enable a software project manager to assess the status of an ongoing project, track potential risks, uncover problem areas before they go “critical,” adjust work flow or tasks, and evaluate the project team’s ability to control quality of software work products.
Project metrics on most software projects occurs during estimation.
Metrics collected from past projects are used as a basis from which effort and time estimates are made for current software work. Production rates represented in terms of models created, review hours, function points, and delivered source lines are measured.
These metrics are used to minimize the development schedule by making the adjustments necessary to avoid delays and mitigate potential problems and risks.
Project metrics are used to assess product quality on an ongoing basis and, when necessary, modify the technical approach to improve quality.
Unit 3

## Slide 20: Software Project Estimations
Software Project Management begins with a set of activities that are collectively called project planning.
The overall goal of project planning is to establish a pragmatic strategy for controlling, tracking, and monitoring a complex technical project.
Why?
So the end result gets done on time, with quality!
Unit 3

## Slide 21: Project Planning Task Set-I
Establish project scope
Determine feasibility
Analyze risks
  Risk analysis is considered in detail in Chapter 25.
Define required resources
  Determine require human resources
  Define reusable software resources
  Identify environmental resources
Unit 3

## Slide 22: Project Planning Task Set-II
Estimate cost and effort
  Decompose the problem
  Develop two or more estimates using size, function points, process tasks or use-cases
  Reconcile the estimates
Develop a project schedule
  Scheduling is considered in detail in Chapter 27.
    Establish a meaningful task set
    Define a task network
    Use scheduling tools to develop a timeline chart
    Define schedule tracking mechanisms
Unit 3

## Slide 23: Estimation
Estimation of resources, cost, and schedule for a software engineering effort requires
  experience
  access to good historical information (metrics)
  the courage to commit to quantitative predictions when qualitative information is all that exists
Estimation carries inherent risk and this risk leads to uncertainty
Unit 3

## Slide 24: Project Estimation
Project scope must be understood
Elaboration (decomposition) is necessary
Historical metrics are very helpful
At least two different techniques should be used
Uncertainty is inherent in the process
Unit 3

## Slide 25: Estimation Accuracy
Predicated on …
  the degree to which the planner has properly estimated the size of the product to be built
  the ability to translate the size estimate into human effort, calendar time, and dollars (a function of the availability of reliable software metrics from past projects)
  the degree to which the project plan reflects the abilities of the software team
  the stability of product requirements and the environment that supports the software engineering effort.
Unit 3

## Slide 26: Functional Decomposition
functional
decomposition
Statement
of
Scope
Perform a Grammatical “parse”
Unit 3

## Slide 27: Conventional Methods: LOC/FP Approach
compute LOC/FP using estimates of information domain values
use historical data to build estimates for the project.
A three-point or expected value can then be computed. The expected value for the estimation variable (size) S can be computed as a weighted average of the optimistic (Sopt), most likely (Sm), and pessimistic (Spess) estimates.
S = Sopt+4Sm+Spess
6
Unit 3

## Slide 28: Example: LOC Approach
Average productivity for systems of this type = 620 LOC/pm.
Burdened labor rate =$8000 per month, the cost per line of code is approximately $13.
Based on the LOC estimate and the historical productivity data, the total estimated project cost is $431,000 and the estimated effort is 54 person-months.
Unit 3

## Slide 29: Example: FP Approach
The estimated number of FP is derived:
FPestimated = count-total 3 [0.65 + 0.01 3 S (Fi)]
FPestimated = 375
organizational average productivity = 6.5 FP/pm.
burdened labor rate = $8000 per month, approximately $1230/FP.
Based on the FP estimate and the historical productivity data, total estimated project cost is $461,000 and estimated effort is 58 person-months.
Unit 3

## Slide 30: Process-Based Estimation
Obtained from “process framework”
application
functions
framework activities
Effort required to accomplish
each framework activity for each application function
Unit 3

## Slide 31: Process-Based Estimation Example
Based on an average burdened labor rate of $8,000 per month, the total estimated project cost is $368,000 and the estimated effort is 46 person-months.
Unit 3

## Slide 32: Tool-Based Estimation
project characteristics
calibration factors
LOC/FP data
Unit 3

## Slide 33: Use-Case–Oriented Metrics
Like FP, the use case is defined early in the software process, allowing it to be used for estimation before significant modeling and construction activities are initiated.
Use cases describe (indirectly, at least) user-visible functions and features that are basic requirements for a system. The use case is independent of programming language.
Because use cases can be created at vastly different levels of abstraction, there is no standard “size” for a use case.
Without a standard measure of what a use case is, its application as a normalization measure (e.g., effort expended per use case) is suspect.
Unit 3

## Slide 34: Empirical Estimation Models
General form:
effort = tuning coefficient * size
exponent
usually derived
as person-months
of effort required
either a constant or
a number derived based
on complexity of project
usually LOC but
may also be
function point
empirically
derived
Unit 3

## Slide 35: COCOMO (constructive cost model)-II
COCOMO II is actually a hierarchy of estimation models that address the following areas:
    Application composition model. Used during the early stages of software engineering, when prototyping of user interfaces, consideration of software and system interaction, assessment of performance, and evaluation of technology maturity are paramount.
    Early design stage model. Used once requirements have been stabilized and basic software architecture has been established.
    Post-architecture-stage model. Used during the construction of the software.
Unit 3

## Slide 36: The Software Equation
A dynamic multivariable model
E = [LOC x B0.333/P]3 x (1/t4)
where
E = effort in person-months or person-years
t = project duration in months or years
B = “special skills factor”
P = “productivity parameter”
Unit 3

## Slide 37
The basic COCOMO model gives an approximate estimate of the project parameters. The basic COCOMO estimation model is given by following expressions:
Effort = a1 x (KLOC)a2 PM (person Month)
Time of Development = b1 x (Effort) b2 Months
Where, a1,a2,b1,b2 are constants for each category of software products
Estimation of Effort
Organic: Effort = 2.4 (KLOC) 1.05 PM
Semi-detached: Effort = 3.0 (KLOC) 1.12 PM
Embedded: Effort = 3.6 (KLOC) 1.20 PM
Estimation Time of Development
Organic: Time of Development = 2.5 (Effort) 0.38 Months
Semi-detached: Time of Development = 2.5 (Effort) 0.35 Months
Embedded: Time of Development = 2.5 (Effort) 0.32 Months
Unit 3

## Slide 38: Organic, Semidetached and Embedded software projects
Organic: A development project can be considered of organic type, if the project deals with developing a well understood application program, the size of the development team is reasonably small, and the team members are experienced in developing similar types of projects.
Semidetached: A development project can be considered of semidetached type, if the development consists of a mixture of experienced and inexperienced staff. Team members may have limited experience on related systems but may be unfamiliar with some aspects of the system being developed.
Embedded: A development project is considered to be of embedded type, if the software being developed is strongly coupled to complex hardware, or if the stringent regulations on the operational procedures exist.

## Slide 39: Example:
Assume that the size of an organic s/w product has been estimated to be 32,000 lines of source code. Assume that the average salary of software be Rs. 15,000/- month. Determine the effort required to develop the software product and the nominal development time.
  Effort= 2.4 x (32) 1.05 = 91 PM
  Time of development = 2.5 x (91) 0.38 = 14 months
  Cost= 14 x 15,000 = Rs. 2,10,000/-
Unit 3

## Slide 40: Project scheduling & Tracking
The scheduling principles:
  compartmentalization—define distinct tasks
  interdependency—indicate task interrelationship
  effort validation—be sure resources are available
  defined responsibilities—people must be assigned
  defined outcomes—each task must have an output
  defined milestones—review for quality
Unit 3

## Slide 41: Effort and Delivery Time
Unit 3

## Slide 42: Effort Allocation
“front end” activities
  customer communication
  analysis
  design
  review and modification
construction activities
  coding or code generation
testing and installation
  unit, integration
  white-box, black box
  regression
40-50%
30-40%
15-20%
Unit 3

## Slide 43: Defining Task Sets
determine type of project
assess the degree of rigor required
identify adaptation criteria
select appropriate software engineering tasks
Unit 3

## Slide 44: Task Set Refinement
1.1 Concept scoping determines the overall scope of the project.
Task definition: Task 1.1 Concept Scoping
1.1.1 Identify need, benefits and potential customers;
1.1.2 Define desired output/control and input events that drive the application;
Begin Task 1.1.2
1.1.2.1 FTR: Review written description of need
  FTR indicates that a formal technical review (Chapter 26) is to be conducted.
1.1.2.2 Derive a list of customer visible outputs/inputs
1.1.2.3 FTR: Review outputs/inputs with customer and revise as required;
endtask Task 1.1.2
1.1.3 Define the functionality/behavior for each major function;
Begin Task 1.1.3
1.1.3.1 FTR: Review output and input data objects derived in task 1.1.2;
1.1.3.2 Derive a model of functions/behaviors;
1.1.3.3 FTR: Review functions/behaviors with customer and revise as required;
endtask Task 1.1.3
1.1.4 Isolate those elements of the technology to be implemented in software;
1.1.5 Research availability of existing software;
1.1.6 Define technical feasibility;
1.1.7 Make quick estimate of size;
1.1.8 Create a Scope Definition;
endTask definition: Task 1.1
is refined to
Unit 3

## Slide 45: Define a Task Network
Unit 3

## Slide 46: Timeline Charts
Tasks
Week 1
Week 2
Week 3
Week 4
Week n
Task 1
Task 2
Task 3
Task 4
Task 5
Task 6
Task 7
Task 8
Task 9
Task 10
Task 11
Task 12
Unit 3

## Slide 47: Use Automated Tools to Derive a Timeline Chart
Unit 3

## Slide 48: Schedule Tracking
  conduct periodic project status meetings in which each team member reports progress and problems.
  evaluate the results of all reviews conducted throughout the software engineering process.
  determine whether formal project milestones (the diamonds) have been accomplished by the scheduled date.
  compare actual start-date to planned start-date for each project task listed in the resource table.
  meet informally with practitioners to obtain their subjective assessment of progress to date and problems on the horizon.
  use earned value analysis to assess progress quantitatively.
Unit 3

## Slide 49: Earned Value Analysis (EVA)
Earned value
  is a measure of progress
  enables us to assess the “percent of completeness” of a project using quantitative analysis rather than rely on a gut feeling
  “provides accurate and reliable readings of performance from as early as 15 percent into the project.” [Fle98]
Unit 3

## Slide 50: Progress on an OO Project-I
Technical milestone: OO analysis completed
    All classes and the class hierarchy have been defined and reviewed.
    Class attributes and operations associated with a class have been defined and reviewed.
    Class relationships have been established and reviewed.
    A behavioral model has been created and reviewed.
    Reusable classes have been noted.
Technical milestone: OO design completed
    The set of subsystems has been defined and reviewed.
    Classes are allocated to subsystems and reviewed.
    Task allocation has been established and reviewed.
    Responsibilities and collaborations have been identified.
    Attributes and operations have been designed and reviewed.
    The communication model has been created and reviewed.

## Slide 51: Progress on an OO Project-II
Technical milestone: OO programming completed
    Each new class has been implemented in code from the design model.
    Extracted classes (from a reuse library) have been implemented.
    Prototype or increment has been built.
Technical milestone: OO testing
    The correctness and completeness of OO analysis and design models has been reviewed.
    A class-responsibility-collaboration network (Chapter 6) has been developed and reviewed.
    Test cases are designed and class-level tests (Chapter 19) have been conducted for each class.
    Test cases are designed and cluster testing (Chapter 19) is completed and the classes are integrated.
    System level tests have been completed.

## Slide 52: Computing Earned Value-I
The budgeted cost of work scheduled (BCWS) is determined for each work task represented in the schedule.
  BCWSi is the effort planned for work task i.
  To determine progress at a given point along the project schedule, the value of BCWS is the sum of the BCWSi values for all work tasks that should have been completed by that point in time on the project schedule.
The BCWS values for all work tasks are summed to derive the budget at completion, BAC. Hence,
BAC = ∑ (BCWSk) for all tasks k

## Slide 53: Computing Earned Value-II
Next, the value for budgeted cost of work performed (BCWP) is computed.
  The value for BCWP is the sum of the BCWS values for all work tasks that have actually been completed by a point in time on the project schedule.
“the distinction between the BCWS and the BCWP is that the former represents the budget of the activities that were planned to be completed and the latter represents the budget of the activities that actually were completed.” [Wil99]
Given values for BCWS, BAC, and BCWP, important progress indicators can be computed:
    Schedule performance index, SPI = BCWP/BCWS
    Schedule variance, SV = BCWP – BCWS
    SPI is an indication of the efficiency with which the project is utilizing scheduled resources.

## Slide 54: Computing Earned Value-III
Percent scheduled for completion = BCWS/BAC
  provides an indication of the percentage of work that should have been completed by time t.
Percent complete = BCWP/BAC
  provides a quantitative indication of the percent of completeness of the project at a given point in time, t.
Actual cost of work performed, ACWP, is the sum of the effort actually expended on work tasks that have been completed by a point in time on the project schedule. It is then possible to compute
    Cost performance index, CPI = BCWP/ACWP
    Cost variance, CV = BCWP – ACWP
Unit 3

## Slide 55: Risk management
A risk is a potential problem – it might happen and it might not
Conceptual definition of risk
– Risk concerns future happenings
– Risk involves change in mind, opinion, actions, places, etc.
– Risk involves choice and the uncertainty that choice entails
Two characteristics of risk:
  Uncertainty – the risk may or may not happen, that is, there are no 100% risks (those, instead, are called constraints)
  Loss – the risk becomes a reality and unwanted consequences or losses occur
Unit 3

## Slide 56: Categories of Risk
Project risks
– They threaten the project plan . If they become real, it is likely that the project schedule will slip and that costs will increase.
Technical risks
– They threaten the quality and timeliness of the software to be produced. If they become real, implementation may become difficult or impossible
Business risks
-They threaten the feasibility of the software to be built. If they become real, they threaten the project or the product
Known risks
– Those risks that can be uncovered after careful evaluation of the project plan, the business and technical environment in which the project is being developed, and other reliable information sources (e.g., unrealistic delivery date)
Unit 3

## Slide 57: Contd…
Predictable risks
– Those risks that are deduced from past project experience (e.g., past turnover)
Unpredictable risks
– Those risks that can and do occur, but are extremely difficult to identify in advance
Unit 3

## Slide 58: Sub-Categories of risk
Market risk – building an excellent product or system that no one really wants
Strategic risk – building a product that no longer fits into the overall business strategy for the company
Sales risk – building a product that the sales force doesn’t understand how to sell
Management risk – losing the support of senior management due to a change in focus or a change in people
Budget risk – losing budgetary or personnel commitment
Unit 3

## Slide 59: Risk Identification
One method for identifying risks is to create a risk item checklist.
The checklist can be used for risk identification and focuses on some subset of known and predictable risks in the following generic subcategories:
  Product size—risks associated with the overall size of the software to be built or modified.
  Business impact—risks associated with constraints imposed by management or the marketplace.
  Stakeholder characteristics—risks associated with the sophistication of the stakeholders and the developer’s ability to communicate with stakeholders in a timely manner.

## Slide 60: Contd…
  Process definition—risks associated with the degree to which the software process has been defined and is followed by the development organization.
  Development environment—risks associated with the availability and quality of the tools to be used to build the product.
  Technology to be built—risks associated with the complexity of the system to be built and the “newness” of the technology that is packaged by the system.
  Staff size and experience—risks associated with the overall technical and project experience of the software engineers who will do the work.
Unit 3

## Slide 61: Assessing Project Risk
Have top software and customer managers formally committed to support the project?
Are end-users enthusiastically committed to the project and the system/product to be built?
Are requirements fully understood by the software engineering team and their customers?
Have customers been involved fully in the definition of requirements?
Do end-users have realistic expectations?
Unit 3

## Slide 62: Contd..
Is project scope stable?
Does the software engineering team have the right mix of skills?
Are project requirements stable?
Does the project team have experience with the technology to be implemented?
Is the number of people on the project team adequate to do the job?
Do all customer/user constituencies agree on the importance of the project and on the requirements for the system/product to be built?
Unit 3

## Slide 63: Risk Components
performance risk—the degree of uncertainty that the product will meet its requirements and be fit for its intended use.
cost risk—the degree of uncertainty that the project budget will be maintained.
support risk—the degree of uncertainty that the resultant software will be easy to correct, adapt, and enhance.
schedule risk—the degree of uncertainty that the project schedule will be maintained and that the product will be delivered on time.
Unit 3

## Slide 64: Risk Projection
Steps of Risk Projection/risk estimation are as follows:
Establish a scale that reflects the perceived likelihood of a risk (e.g., 1-low, 10-high)
Explain the consequences of the risk
Estimate the impact of the risk on the project and product
Note the overall accuracy of the risk projection so that there will be no misunderstandings
Unit 3

## Slide 65: Building a Risk Table
Risk
Probability
Impact
RMMM
Risk
Mitigation
Monitoring
&
Management
Unit 3

## Slide 66: Building the Risk Table
Estimate the probability of occurrence
Estimate the impact on the project on a scale of 1 to 5, where
  1 = low impact on project success
  5 = catastrophic impact on project success
sort the table by probability and impact
Unit 3

## Slide 67: Risk Exposure (Impact)
The overall risk exposure, RE, is determined using the following relationship [Hal98]:
RE = P x C
where
P is the probability of occurrence for a risk, and
C is the cost to the project should the risk occur.
Unit 3

## Slide 68: Risk Exposure Example
Risk identification. Only 70 percent of the software components scheduled for reuse will, in fact, be integrated into the application. The remaining functionality will have to be custom developed.
Risk probability. 80% (likely).
Risk impact. 60 reusable software components were planned. If only 70 percent can be used, 18 components would have to be developed from scratch (in addition to other custom software that has been scheduled for development). Since the average component is 100 LOC and local data indicate that the software engineering cost for each LOC is $14.00, the overall cost (impact) to develop the components would be 18 x 100 x 14 = $25,200.
Risk exposure. RE = 0.80 x 25,200 ~ $20,200.

## Slide 69: Risk Mitigation, Monitoring, and Management
Risk mitigation (proactive planning for risk avoidance)
Risk monitoring (assessing whether predicted risks occur or not, ensuring risk aversion steps are being properly applied, collect information for future risk analysis, attempt to determine which risks caused which problems)
Risk management and contingency planning (actions to be taken in the event that mitigation steps have failed and the risk has become a live problem)
The goal of the risk mitigation, monitoring and management plan is to identify as many potential risks as possible.
Unit 3

## Slide 70: Contd…
When all risks have been identified, they will then be evaluated to determine their probability of occurrence.
Plans will then be made to avoid each risk, to track each risk to determine if it is more or less likely to occur, and to plan for those risks should they occur.
It is the organization’s responsibility to perform risk mitigation, monitoring, and management in order to produce a quality product.
The quicker the risks can be identified and avoided, the smaller the chances of having to face that particular risk’s consequence.
The fewer consequences suffered as a result of good RMMM plan, the better the product, and the smoother the development process.
Unit 3

## Slide 71: Risk Mitigation
To mitigate this risk, you would develop a strategy for reducing turnover.
Among the possible steps to be taken are:
Meet with current staff to determine causes for turnover (e.g., poor working conditions, low pay, and competitive job market).
Mitigate those causes that are under your control before the project starts.
Once the project commences, assume turnover will occur and develop techniques to ensure continuity when people leave.
Unit 3

## Slide 72: Contd…
Organize project teams so that information about each development activity is widely dispersed.
Define work product standards and establish mechanisms to be sure that all models and documents are developed in a timely manner.
Conduct peer reviews of all work (so that more than one person is “up to speed”).
Assign a backup staff member for every critical technologist.
Unit 3

## Slide 73: Risk Monitoring
The project manager monitors factors that may provide an indication of whether the risk is becoming more or less likely.
In the case of high staff turnover, the general attitude of team members based on project pressures, the degree to which the team has jelled, inter-personal relationships among team members, potential problems with compensation and benefits, and the availability of jobs within the company and outside it are all monitored.
In addition to monitoring these factors, a project manager should monitor the effectiveness of risk mitigation steps.
The project manager should monitor work products carefully to ensure that each can stand on its own and that each imparts information that would be necessary if a newcomer were forced to join the software team somewhere in the middle of the project.

## Slide 74: Risk Management
Risk management and contingency planning assumes that mitigation efforts have failed and that the risk has become a reality.
If the mitigation strategy has been followed, backup is available, information is documented, and knowledge has been dispersed across the team.
In addition, you can temporarily refocus resources (and readjust the project schedule) to those functions that are fully staffed, enabling newcomers who must be added to the team to “get up to speed.” Those individuals who are leaving are asked to stop all work and spend their last weeks in “knowledge transfer mode.”
Unit 3

## Slide 75: Risk Due to Product Size
• estimated size of the product in LOC or FP?
• estimated size of product in number of programs,
files, transactions?
• percentage deviation in size of product from
average for previous products?
• size of database created or used by the product?
• number of users of the product?
• number of projected changes to the requirements
for the product? before delivery? after delivery?
• amount of reused software?
Attributes that affect risk:
Unit 3

## Slide 76: Risk Due to Business Impact
• affect of this product on company revenue?
• visibility of this product by senior management?
• reasonableness of delivery deadline?
• number of customers who will use this product
• interoperability constraints
• sophistication of end users?
• amount and quality of product documentation that
must be produced and delivered to the customer?
• governmental constraints
• costs associated with late delivery?
• costs associated with a defective product?
Attributes that affect risk:
Unit 3

## Slide 77: Risks Due to the Customer
• Have you worked with the customer in the past?
• Does the customer have a solid idea of requirements?
• Has the customer agreed to spend time with you?
• Is the customer willing to participate in reviews?
• Is the customer technically sophisticated?
• Is the customer willing to let your people do their
job—that is, will the customer resist looking over your
shoulder during technically detailed work?
• Does the customer understand the software
engineering process?
Questions that must be answered:
Unit 3

## Slide 78: Risks Due to Process Maturity
• Have you established a common process framework?
• Is it followed by project teams?
• Do you have management support for
software engineering
• Do you have a proactive approach to SQA?
• Do you conduct formal technical reviews?
• Are CASE tools used for analysis, design and
testing?
• Are the tools integrated with one another?
• Have document formats been established?
Questions that must be answered:
Unit 3

## Slide 79: Technology Risks
• Is the technology new to your organization?
• Are new algorithms, I/O technology required?
• Is new or unproven hardware involved?
• Does the application interface with new software?
• Is a specialized user interface required?
• Is the application radically different?
• Are you using new software engineering methods?
• Are you using unconventional software development
methods, such as formal methods, AI-based approaches,
artificial neural networks?
• Are there significant performance constraints?
• Is there doubt the functionality requested is "do-able?"
Questions that must be answered:
Unit 3

## Slide 80: RMMM Plan
A risk management strategy can be included in the software project plan, or the risk management steps can be organized into a separate risk mitigation, monitoring and management plan (RMMM Plan)
This plan documents all work performed as part of risk analysis and is used by the project manager as a part of overall project plan.
Some software teams do not develop a formal RMMM document , rather the risk is documented individually using a risk information sheet (RIS).
Unit 3

## Slide 81: Contd…
RIS includes:
  Risk ID
  Date
  Probability
  Impact
  Description
  Refinement
  Mitigation / Monitoring
  Management / contigency plan / trigger
  Current status
Unit 3

## Slide 82: RIS Sample
Unit 3